## smoke test
Milestone | What is included | Pass/Fail | Notes | correction need to be applied
Pre-Power Inspection Complete | Visual inspection + continuity checks (no shorts on any rail / USB / GND) | Pass
Safe Power First Apply | 5V applied with current limit (500mA) and no abnormal current draw | Pass | power consumption : 74mA
Power Rails Verified | Buck (5V → 3.6V) and LDO (3.6V → 3.3V) stable under no-load/light-load conditions | Correct successfully | 3.3V = 2.261 v
Reversed power test | test every power entry with a reversed voltage | Not for this board
Passive Components Verified | LEDs, pull-ups, and GPIO loading confirmed safe and non-sagging | Pass
GNSS Module Power-Up Successful | Module powers correctly at 3.3V, no overheating, reset line stable | Pass
GNSS UART Output Verified | NMEA or binary output visible via USB-UART adapter | Pass
USB Interface Functional | USB-C enumerates on PC, no CC/D+/D− issues, no overheating | Pass
RF & Antenna Path Verified | Antenna connected, no shorts, optional active bias works correctly | Correct successfully
Satellite Fix Achieved | GNSS lock obtained and stable satellite tracking confirmed | Pass
System End-to-End Validation | Full system working via USB with continuous GNSS data output | Pass
,

## Interface
Interfaces | Device | Pass/Fail | Notes
5V power (TP11) | (protection line / ideal diode) |  | = 4,97V (The board still working with low value 4.5 V)
3.7V power (TP14) | MPM3632CGQV-Z |  | = 3.66V
3.3V DIG power (TP13) | TPS7A9401DSCR (U7) |  | = 3.31V
3.3V RF power (TP14) | TPS7A9401DSCR (U12) |  | = 3.30V
1.8V Mag power line (TP15) | MP2002AGD-Z_C3751012
UART1 (internal) | G5 |  | Data is send to the STM32
UART2 (J4) | G5
UART1 (internal) | STM32 or NXP |  | Data is received by STM32
UART2 (external) pads | STM32 or NXP
I²C (J7) | STM32 or NXP
CAN (J6) (J9) | STM32 or NXP+ Tranceiver
I²C (internal) | STM32 or NXP+ Mag
PPS1 (J1) (D6) | G5
Events_A (J1) | G5
GPIO1 (D2) | G5
Position | G5
RTK | G5
Heading | G5
|  |  |  | N° | Type | Device | Connectors
|  |  |  | 1 | Antenna | G5 P3(H) | MMCX male plug
|  |  |  | 2 | PPS/EVENT | G5 P3(H) | JST 3 pin / DF40
|  |  |  | 3 | I²C 1 | NXP MCU() [I²C 1] | JST 4 pin
|  |  |  | 4 | UART (RTS/CTS) G5 | G5 P3(H) [UART 2 – shared with interface 8] | JST 6 pin / DF40
|  |  |  | 5 | USB-2.0 | G5 P3(H) | USB-C
|  |  |  | 6 | CAN 11 | NXP MCU + Transceiver (TJA1462ATK) | x2 JST 4 pin
|  |  |  | 7 | SPI1 | Magnetometer STM (LIS2MDLTR) | x4 Solder pads
|  |  |  | 8 | UART (RTS/CTS) G5 + PPS/EVENT1 | G5 P3(H) [UART 2 – shared with interface 3 and 4] | DF40 / JST 6 pin + JST 3 pin
|  |  |  | 9 | UART NXP | NXP MCU [UART 2] | x4 Solder pads
|  |  |  | * | UART G5 | G5 P3(H) [UART 1] <-> NXP [USART 1] | Internal connection

## Devices
Devices | Pass/Fail | Notes
STM32G473 or MCXA154VLH | ok | No over heating
Mag LIS2MDL or BMM350 | ok | Provide data trough SPI
Transceiver CAN | ok | Send data
Mosaic G5 | ok | No over heating (<50°) provide position

## Performance Test GNSS
Perfomance test to compare G5Fly and Mosaic-GO
make sure they work on same version
Standalone fixed test (min 12h)
RTK fixed test (min 12h)
Heading + RTK test (30 min in movement)
Data to log and graph to compare
height
C\N
heading
PVT mode
PosCovcartesian
AttEULER
PosCovGeodetic or PosCovcartesian
AttCovEuler
C/N over time
RTK stats pie chart attitude
PVT mode over time
Height
NMEA(GGA)
NMEA(HDT): Heading
NMEA(HDG)
PPS
Events
Note on A9: Théophile Raimbault: Is recommanded to log all the data but only treat the graph you will need

## Avreage Quality indicators
Calculate average indicator on this value
Main RF power
Aux1 RF power
Main signals
Aux1 signals
CPU
Scintillation
Base measurements
Overall
C/N ratio
AGC table value
Note on A1: Théophile Raimbault: Is recommanded to log all the data but only treat the graph you will need